## GANTT CHART
PROJECT | Brain 4ce | [5 empty] | CLASS | [11 empty] | ECE Senior Design
TEAM LEAD | Brendan (9/27 - 10/25), Alex (10/25 - 11/22), Jonathan (11/22 - ) | [5 empty] | DATE | [11 empty] | Fall 2022/ Spring 2023
[41 empty] | PHASE 4 | [32 empty] | PHASE 6
[10 empty] | PHASE 1 | [10 empty] | PHASE 2 | [12 empty] | PHASE 3 | [7 empty] | ↓ | PHASE 5 | [30 empty] | PHASE 7 | [20 empty] | PHASE 8
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | COMPLETION DATE | DUE DATE | DURATION (days) | PCT OF TASK COMPLETE |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15
 | time axis 2022-11-27 to 2023-03-11
 | time axis 2022-11-27 to 2023-03-11
1 | Problem Solving/ Finalizing Headset
1.1 | Order PCB parts | Mitchell | 2022-11-29 | 2022-12-02 | 2022-12-09 | 3 | 100%
1.2 | Buy components for headset (probes, springs, etc) | Brendan/Jonathan | 2022-11-29 | 2022-12-08 | 2022-12-09 | 9 | 100%
1.3 | Finish printing components for headset | Brendan | 2022-11-29 | 2022-12-10 | 2022-12-09 | 11 | 100%
1.4 | Program Interface betwenn Arduino and PCB | Alex | 2022-11-29 |  | 2022-12-16 | N/A | 50% | bar: 2022-12-12; 2022-12-14
2 | EEG Assembly
2.1 | Solder PCB | Mitchell | 2022-12-10 |  | 2022-12-22 | N/A | 0%
2.2 | Assemble headset | Brendan | 2022-12-10 |  | 2022-12-22 | N/A | 0%
3 | Data Collection
3.1 | Collect Data from EEG | Mitchell/Brendan | 2022-12-23 |  | 2022-12-30 | N/A | 0%
3.2 | Label EEG data | Mitchell/Brendan | 2022-12-23 |  | 2022-12-30 | N/A | 0%
4 | Transfer Data for ML Algorithm
4.2 | Forward data to ML lead | Mitchell | 2022-12-31 |  | 2022-12-31 | N/A | 0%
5 | ML Algorithm/ Schematic Redesign
5.1 | Complete redesign schematic | Mitchell | 2023-01-01 |  | 2023-01-31 | N/A | 0%
5.2 | Layout redesigned EEG | Mitchell | 2023-01-01 |  | 2023-01-31 | N/A | 0%
5.3 | Design and train ML algorithm | Dayanna | 2023-01-01 |  | 2023-01-31 | N/A | 0%
5.4 | Test ML Algorithm | Dayanna | 2023-01-01 |  | 2023-01-31 | N/A | 0%
5.5 | Improve signal processing for ML algorithm | Mitchell/Dayanna | 2023-01-01 |  | 2023-01-31 | N/A | 0%
5.6 | Build virtual environment | Jonathan | 2023-01-01 |  | 2023-01-31 | N/A | 0%
6 | Redesign Stage
6.1 | Fabricate redesign | Brendan/Mitchell | 2023-02-01 |  | 2023-02-07 | N/A | 0%
6.2 | Assemble redesign | Brendan/Mitchell | 2023-02-01 |  | 2023-02-07 | N/A | 0%
7 | Integration Stage
7.1 | Interface EEG with ML Algorithm in real time | Alex/Dayanna | 2023-01-01 |  | 2023-01-31 | N/A | 0%
7.2 | Get NN to work live (feed dataset) | Dayanna/Jonathan | 2023-02-01 |  | 2023-02-21 | N/A | 0%
7.3 | Design interface between NN and virtual environment | Dayanna/Jonathan | 2023-02-01 |  | 2023-02-21 | N/A | 0%
7.4 | Get NN/ virtual environment interface to work live | Dayanna/Jonathan | 2023-02-01 |  | 2023-02-21 | N/A | 0%
8 | Finalization Stage
8.1 | Set up NN/virtual environment to receive live data from headset | Dayanna/Jonathan/Alex | 2023-02-22 |  | 2023-03-07 | N/A | 0%
8.2 | Test and Debug | everyone | 2023-02-22 |  | 2023-03-07 | N/A | 0%
9 | Moving Forward
9.1 | Explore further applications of project | everyone | 2023-03-08 |  | 2023-05-05 | N/A | 0%
9.2 | RC Car Demo - ECE Day (optional) | everyone | 2023-03-08 |  | 2023-05-05 | N/A | 0%